YUVA MACHINE LEARNING ENGINEER INTERNSHIP

Professional Project Plan & Implementation Roadmap

Project: AI-Powered Resume Intelligence & Job Matching System
Duration: 6 Weeks | Planned Effort: 30–35 Hours
Technology Focus: Python • NLP • Machine Learning • FastAPI • Database • Docker

Table of Contents

· Professional introduction

· Research & ideation

· Literature/public-information review

· Detailed problem statement

· Inputs, outputs, scope and challenges

· Project objectives

· End-to-end ML architecture

· Data strategy and preprocessing

· NLP + ML model development

· Baseline vs semantic matching

· Skill-gap and recommendation engine

· Evaluation metrics and acceptance criteria

· 6 weeks implementation timelines

· Weekly milestones and deliverables

· Critical path and dependencies

· Software, libraries, hardware and human resources

· Detailed risk-management table

· Documentation and GitHub project structure

· Strategic implementation road-map

· Expected outcomes

· Conclusion

· References

· Final submission checklist

# 1. Introduction

This report presents a six-week Machine Learning Engineering project plan for an AI-Powered Resume Intelligence and Job Matching System. The project is designed for a YUVA internship environment and follows an end-to-end machine learning lifecycle: research and ideation, problem definition, data acquisition, data preparation, model development, evaluation, API development, deployment planning, testing, documentation, and final presentation.

The proposed system will process a candidate resume and a job description, extract relevant information such as skills, education, and experience, measure semantic and skill-based compatibility, identify skill gaps, and provide explainable recommendations. The project is intentionally structured as an ML engineering project rather than only a model-training exercise.

The final prototype will use Python-based NLP and machine-learning components, expose inference through FastAPI, store structured information in a database, and use Docker for reproducible deployment. The project will emphasize reproducibility, measurable evaluation, clean software architecture, and responsible handling of candidate data.

# 2. Research & Ideation

The first phase establishes the technical and business rationale for automated resume-job matching. Traditional keyword matching can miss semantically equivalent skills and may produce weak results when job descriptions and resumes use different terminology. Modern NLP systems can represent text as numerical embeddings, enabling semantic similarity beyond exact keyword overlap.

## 2.1 Literature and Public-Information Review

| Research area | Relevant insight | Project implication |
| --- | --- | --- |
| Information retrieval | TF-IDF and cosine similarity provide a transparent lexical baseline. | Build a measurable baseline before using embeddings. |
| Sentence embeddings | Transformer-based embeddings can represent semantic relationships between text segments. | Use embeddings for semantic matching and comparison. |
| Named/entity information extraction | Skills and structured entities can be extracted from unstructured text. | Create a normalized skill representation for matching. |
| Learning-to-rank / recommendation | Candidate-job matching can be treated as a ranking problem. | Evaluate top-k recommendations rather than accuracy alone. |
| MLOps / ML engineering | Reproducibility, testing, versioning, monitoring and deployment are part of production ML. | Include API, Docker, logging, tests and model versioning in the project. |

## 2.2 Ideation Outcome

The selected problem is resume-to-job matching because it combines NLP, machine learning, information retrieval, recommendation logic, backend engineering, and deployment. It is sufficiently complex for a six-week internship while remaining feasible as a demonstrable prototype.

### Concrete example and evidence plan:

Example input pair: a resume containing “Python, Django, REST API, PostgreSQL and Docker” and a job description requiring “Python, FastAPI, PostgreSQL, Docker and AWS.”

Expected evidence: the system should identify Python, PostgreSQL and Docker as matched skills, FastAPI and AWS as missing skills, and report separate lexical, semantic and skill-coverage signals.

The experiment log will preserve representative examples, model configuration, dataset version, similarity scores and reviewer observations so that results can be reproduced rather than described only qualitatively.

# 3. Problem Definition

Recruiters and job seekers frequently need to compare resumes against large numbers of job descriptions. Simple keyword matching can fail when equivalent concepts are expressed differently—for example, 'REST API development' and 'RESTful web services'. The proposed system will create a structured representation of both documents and calculate a transparent, configurable compatibility score.

## 3.1 Problem Statement

Design and implement an NLP-based machine learning system that accepts a resume and a job description, extracts relevant career information, estimates semantic and skill-based compatibility, identifies missing or weakly matched skills, and produces an explainable job-match report through a deployable API.

## 3.2 Inputs

Resume in PDF or supported text format.

Job description in text or PDF format.

Optional structured preferences such as target role or experience range.

System configuration such as embedding model, similarity weights, and recommendation parameters.

## 3.3 Outputs

Overall job-match score.

Matched skills and evidence extracted from the resume.

Missing or weakly matched skills.

Semantic similarity between resume and job-description sections.

Experience/education alignment where reliable structured information is available.

Ranked recommendations for skills or learning areas.

Explainable result summary showing the major factors contributing to the score.

## 3.4 Scope

In scope: resume/JD parsing, NLP preprocessing, skill extraction, lexical baseline, embeddings, scoring, recommendation, evaluation, API, database, Docker and documentation.

Out of scope: autonomous hiring decisions, discrimination-sensitive candidate ranking, background verification, or fully automated recruitment decisions.

The system is a decision-support prototype. Human review remains necessary for actual recruitment decisions.

# 4. Project Objectives

Conduct a focused literature review and define a practical ML engineering use case.

Build a reproducible pipeline for extracting and normalizing information from resumes and job descriptions.

Develop a transparent TF-IDF/cosine-similarity baseline.

Develop a semantic matching component using transformer-based text embeddings.

Create a hybrid scoring mechanism combining lexical, semantic, and skill-based signals.

Implement skill-gap analysis and recommendation logic.

Define an evaluation framework using classification and ranking metrics where labeled data permits.

Develop a FastAPI service for model inference.

Persist relevant structured data and model metadata using a database.

Containerize the application using Docker.

Document the complete ML lifecycle, experiments, limitations, and deployment process.

Demonstrate the final system and provide a clear roadmap for future productionization.

# 5. Proposed System Architecture

The architecture separates data ingestion, NLP processing, model inference, scoring, recommendations, and serving. This modular structure allows individual components to be tested and improved independently.

Resume/JD → File/Text Extraction → Cleaning & Normalization → Skill/Entity Extraction → TF-IDF Baseline + Embedding Model → Hybrid Matching Engine → Skill Gap Analyzer → Recommendation Engine → FastAPI → Database → Web/Client Interface → Docker Deployment

## 5.1 Core Components

| Component | Responsibility |
| --- | --- |
| Document parser | Extract clean text from PDF/text inputs. |
| NLP preprocessor | Normalize text, remove irrelevant artifacts, segment sections. |
| Skill extractor | Identify technical and professional skills using dictionaries, rules and/or NER. |
| Lexical matcher | Calculate TF-IDF and cosine similarity baseline. |
| Semantic matcher | Generate embeddings and calculate semantic similarity. |
| Hybrid scoring engine | Combine skill, lexical and semantic signals. |
| Gap analyzer | Identify job requirements absent or weakly supported in the resume. |
| Recommendation engine | Rank useful skills/learning areas based on detected gaps. |
| FastAPI service | Expose prediction and analysis endpoints. |
| Database | Store analysis metadata, model version, configuration and non-sensitive project records. |
| Docker layer | Provide reproducible application packaging and deployment. |

# 6. Data Strategy

Data quality is a central dependency. The project will use publicly available datasets, synthetic examples, or carefully constructed annotation sets subject to licensing and usage conditions. Personally identifiable candidate information should not be collected unnecessarily.

## 6.1 Data Requirements

Resume/job-description text pairs.

Skill annotations or normalized skill dictionaries where available.

Relevant job-role categories.

Optional relevance labels such as strong match, partial match, or weak match for evaluation.

A documented train/validation/test split where supervised labels are used.

## 6.2 Data Preparation

Collect and document permitted data sources.

Remove or anonymize unnecessary personal identifiers.

Extract text and normalize formatting.

Segment documents into sections such as skills, experience, education and summary.

Normalize skill synonyms and abbreviations.

Remove duplicates and obvious corrupted records.

Create a versioned dataset manifest.

Split data before model tuning to avoid evaluation leakage.

# 7. Machine Learning Development Plan

## 7.1 Baseline Model

The baseline will use TF-IDF vectorization and cosine similarity. This model is deliberately simple and interpretable. It provides a benchmark against which semantic embeddings and the hybrid system can be evaluated.

## 7.2 Semantic Model

A sentence-transformer or comparable embedding model will represent resume and job-description text in a semantic vector space. Similarity can then be measured between document-level or section-level embeddings.

## 7.3 Hybrid Matching Model

The final prototype will combine multiple signals. An example formulation is: Match Score = w1 × semantic similarity + w2 × skill coverage + w3 × lexical similarity + w4 × experience alignment. Weights will be treated as configuration parameters and selected using validation data rather than arbitrarily tuned on the test set.

## 7.4 Recommendation Engine

Identify required skills from the job description.

Compare required skills with normalized candidate skills.

Classify skills as matched, partially matched, or missing where the evidence supports such distinctions.

### Concrete evaluation evidence will include:

A before/after data-quality table showing missing values, duplicates and invalid records removed.

TF-IDF vocabulary size and feature-matrix dimensions, followed by sample cosine-similarity scores for relevant and irrelevant resume/job pairs.

A reviewed skill-extraction sample with matched skills, missed skills and false detections; precision, recall and F1 will be reported where enough reviewed examples are available.

An ablation comparison of lexical-only, skill-only, semantic-only and hybrid scoring to demonstrate whether each component contributes measurable value.

A small error-analysis table containing false positives and false negatives, their likely causes, and the corrective action planned for the next iteration.

Rank missing skills by job relevance and frequency.

Generate a concise skill-gap report rather than making employment decisions.

# 8. Evaluation Framework

Evaluation will distinguish between matching quality and engineering quality. If a sufficiently labeled dataset is available, classification metrics can be used for match categories. For ranking outputs, top-k ranking metrics are more appropriate.

| Metric | Purpose |
| --- | --- |
| Precision | Measures how many predicted relevant matches are actually relevant. |
| Recall | Measures how many relevant matches are successfully retrieved. |
| F1-score | Balances precision and recall. |
| Precision@K | Measures relevance among the top K recommendations. |
| Recall@K | Measures how much of the relevant set appears in the top K results. |
| MRR / NDCG | Optional ranking metrics for ordered recommendations. |
| Cosine similarity distribution | Analyzes semantic matching behavior. |
| Latency | Measures API/model response time. |
| Memory/model size | Measures deployment resource requirements. |
| Error analysis | Identifies systematic failure modes such as synonym, parsing or section errors. |

## 8.1 Acceptance Criteria

The complete pipeline executes reproducibly from documented inputs.

The semantic model provides measurable improvement over or complementary value to the lexical baseline on the selected validation protocol.

The system returns explainable matched and missing-skill information.

The API handles valid and invalid inputs safely.

Model version and configuration are recorded with inference results.

Dockerized deployment runs successfully on the target development environment.

Final evaluation is performed on data not used for model selection.

# 9. Six-Week Implementation Timeline

| Week | Focus | Major Activities | Deliverables / Milestone |
| --- | --- | --- | --- |
| Week 1 | Research, Data & Baseline | Literature/public-information review; finalize problem definition; select and document public datasets; create data dictionary; set up Git/environment; perform initial EDA; define keyword and TF-IDF baseline. | M1: Project charter + research notes + dataset inventory + EDA notebook + architecture + reproducible environment. Evidence: dataset statistics, missing/duplicate counts and initial baseline specification. |
| Week 2 | Data Cleaning & NLP Pipeline | Clean text; remove duplicates/corrupted records; handle missing values; normalize formatting; segment resume/JD sections; normalize skill names and aliases; split data before fitting transformations; implement reusable preprocessing and TF-IDF pipeline. | M2: Versioned clean dataset + preprocessing module + before/after quality report + TF-IDF feature matrix. Evidence: cleaning statistics and leakage-safe split. |
| Week 3 | Baseline ML & Skill Intelligence | Implement cosine similarity; create skill taxonomy; extract skills; calculate skill coverage; create reviewed relevance examples; compare baseline results across sample pairs. | M3: Working baseline + skill extractor + labeled/reviewed evaluation subset + sample score explanations. Evidence: matched/missing skills and baseline similarity results. |
| Week 4 | Hybrid Matching & Evaluation | Generate embeddings; compare semantic vs lexical similarity; build hybrid score; run ablation experiments; tune only on validation data; perform error analysis; finalize evaluation protocol. | M4: Candidate matching engine + evaluation report + ablation table + error-analysis log. Evidence: metric comparison and documented failure cases. |
| Week 5 | ML Engineering & API | Separate preprocessing/inference/API layers; serialize model/vectorizer/artifacts; build FastAPI endpoints and validation; add unit/integration tests; add logging/configuration; Dockerize and run local container smoke tests. | M5: Containerized inference API + API documentation + test results + Docker build/run evidence + architecture diagram. |
| Week 6 | Deployment Readiness, QA & Documentation | Run end-to-end tests; benchmark average/p95 latency and resource use; add health/readiness checks; document model/data/API versions; define monitoring and rollback; prepare deployment guide, model card, final report and demo. | M6: Release candidate + deployment guide + monitoring plan + model card + final report/presentation. Evidence: reproducibility, test results, benchmark and production-readiness checklist. |

## 9.1 Planned Effort

The project is planned around approximately 30–35 hours of focused project work, with the six-week internship providing time for learning, iteration, debugging, review, and mentor feedback. The schedule is intentionally milestone-driven rather than dependent on a single uninterrupted coding block.

# 10. Critical Path and Dependencies

The critical path begins with problem and data definition and ends with deployment validation. The following dependencies must be controlled carefully because failure in an upstream stage can invalidate downstream results.

| Dependency | Reason | Mitigation |
| --- | --- | --- |
| Data availability and quality → NLP | Parsing and matching cannot be validated without suitable text data. | Validate data sources during Week 1 and prepare backup sources. |
| NLP preprocessing → model training | Inconsistent preprocessing creates unreliable features. | Centralize preprocessing in reusable modules and unit tests. |
| Baseline → semantic model | Without a baseline, improvement cannot be measured. | Complete TF-IDF baseline before tuning embeddings. |
| Validation → model selection | Model selection must not use test data. | Freeze test set and record validation decisions. |
| Model → API | Serving must use exactly the same preprocessing and model version. | Package preprocessing and model together with version metadata. |
| API → Docker/deployment | Containerization depends on a stable inference interface. | Complete API contract and integration tests before Docker packaging. |

# 11. Resource Requirements

## 11.1 Software

Python 3.10+

pandas and NumPy

scikit-learn

NLTK/spaCy or equivalent NLP tooling

Sentence Transformers / Hugging Face ecosystem for embeddings

PyMuPDF or equivalent PDF text extraction library

FastAPI and Uvicorn

SQLAlchemy and PostgreSQL or MongoDB, depending on implementation choice

Matplotlib/Plotly for analysis and reporting

pytest for testing

Docker and Git/GitHub

VS Code or Jupyter Notebook

## 11.2 Hardware

Development system with at least 8 GB RAM; 16 GB is preferable for NLP experimentation.

SSD storage for datasets, models, Docker images and logs.

GPU is optional; embedding inference and small-scale model experiments can run on CPU, while GPU can accelerate larger experiments.

Stable internet connection for permitted model/dataset downloads and deployment testing.

## 11.3 Human Resources

Machine Learning Engineer intern: primary implementation and experimentation.

Project mentor/supervisor: weekly technical review and milestone validation.

Optional domain/recruitment reviewer: validates practical interpretation of skill matching.

# 12. Risk Management

| Risk | Probability | Impact | Mitigation / early-warning evidence |
| --- | --- | --- | --- |
| Insufficient labeled resume-job pairs | Medium | High | Early warning: too few usable labeled pairs. Use public/synthetic data with documented labeling rules and create a manually reviewed evaluation subset. |
| PDF parsing failures | Medium | Medium | Early warning: extracted text is empty or unusually short. Use multiple extraction paths, validate text length, flag failed documents and preserve original files only where permitted. |
| Skill synonym/abbreviation mismatch | High | High | Early warning: manual review finds missed skills such as REST/RESTful or PostgreSQL/Postgres. Maintain normalized taxonomy, aliases and embedding-assisted matching; measure extraction quality. |
| Data leakage | Medium | High | Early warning: unusually high validation performance or duplicate pairs across splits. Split before fitting vectorizers/scalers, remove near-duplicates and lock the final test set. |
| Model overfitting | Medium | High | Early warning: validation improves while unseen examples do not. Use validation-only tuning, regularization where applicable, error analysis and one locked final test evaluation. |
| Biased or unfair ranking | Medium | Critical | Early warning: unexpected score differences associated with irrelevant sensitive information. Avoid sensitive attributes, test behavior on appropriate subsets where data permits, and position the tool as decision support rather than automated hiring. |
| Embedding model too large | Medium | Medium | Early warning: excessive RAM or inference latency. Benchmark smaller models, cache reusable embeddings where appropriate and set resource limits. |
| API/deployment errors | Medium | Medium | Early warning: local success but container/API failure. Add automated tests, Docker smoke tests, health endpoint and structured error logging. |
| Privacy/security issue | Medium | Critical | Early warning: PII appearing in logs or persistent temporary files. Prefer anonymized/public data, restrict uploads, use temporary storage, avoid resume text in logs and document retention/access controls. |
| Scope expansion | High | Medium | Early warning: optional features consume milestone time. Freeze the six-week MVP scope and move non-critical features to the roadmap. |

# 13. Documentation & Formatting Plan

Documentation will be maintained throughout the internship rather than written only at the end. The project repository will contain a README, architecture diagram, setup instructions, experiment records, API documentation, test results, and limitations.

## 13.1 Recommended Repository Structure

resume-intelligence-ml/
├── data/
│   ├── raw/
│   ├── processed/
│   └── manifests/
├── notebooks/
├── src/
│   ├── ingestion/
│   ├── preprocessing/
│   ├── extraction/
│   ├── matching/
│   ├── recommendation/
│   └── evaluation/
├── models/
├── api/
│   ├── main.py
│   └── schemas.py
├── tests/
├── docker/
├── reports/
├── requirements.txt
├── Dockerfile
└── README.md

# 14. Strategic Roadmap for Implementation

## Phase 1 – Prototype

Deliver reliable parsing and matching for common resume/JD formats.

Establish baseline and semantic matching performance.

Provide an interpretable skill-gap report.

### Concrete productionization sequence:

- 1. Reproducible packaging — pin dependency versions, move notebook logic into src/, create one inference entry point, and record model/vectorizer versions.

- 2. Automated testing — add unit tests for text cleaning, skill extraction and scoring; add API integration tests and a Docker smoke test.

- 3. Secure API — validate file type/size, sanitize filenames, use temporary storage, keep secrets in environment variables, and prevent resume text from being written to normal logs.

- 4. Container deployment — build and test the Docker image in a clean environment; expose health/readiness endpoints and configure resource limits.

- 5. Staging deployment — deploy the container to a managed cloud environment with HTTPS and environment-specific configuration before any production release.

- 6. Monitoring — track request count, latency, error rate, resource use and model version; use request IDs instead of storing sensitive resume contents.

- 7. Model monitoring — periodically review score distributions, skill-frequency changes and a manually checked quality sample for data/model drift.

- 8. Release and rollback — version every model release, retain the previous working artifact, test new versions in staging, and document rollback commands.

- 9. Continuous improvement — incorporate approved feedback into a versioned evaluation set and only retrain/recalibrate after comparing the new version with the existing baseline.

### Concrete production evidence to retain:

Successful clean-environment installation and Docker build.

API request/response example plus invalid-input test result.

Unit/integration test summary.

Average and p95 inference latency benchmark.

Model/version manifest and configuration record.

Health/readiness check result.

Monitoring and rollback checklist.

## Phase 2 – ML Engineering Maturity

Introduce experiment tracking and model registry practices.

Add automated data/model validation.

Improve API observability and testing.

Add caching and batch inference where useful.

## Phase 3 – Production Readiness

Conduct larger and more representative validation.

Evaluate model behavior across relevant job families and candidate groups.

Introduce secure authentication, access control, encrypted storage and retention policies.

Deploy using a cloud environment with monitoring and rollback capability.

## Phase 4 – Advanced ML

Learning-to-rank models using high-quality relevance labels.

Domain-adapted embeddings.

Feedback loops for recruiter/user corrections.

Drift monitoring and periodic model evaluation.

Multilingual resume and job-description support.

# 15. Expected Outcomes

A complete, reproducible NLP/ML pipeline.

A documented baseline and semantic matching model.

A hybrid job-matching and skill-gap engine.

A working FastAPI inference service.

Database-backed project metadata.

Dockerized deployment package.

Automated tests and evaluation evidence.

Professional technical documentation and final internship presentation.

A strong portfolio artifact demonstrating both machine-learning and software-engineering capabilities.

# 16. Conclusion

The proposed AI-Powered Resume Intelligence and Job Matching System is structured as a six-week Machine Learning Engineering internship project with a clear progression from research to deployment. It combines NLP, information retrieval, semantic embeddings, recommendation logic, model evaluation, API engineering, databases, testing, and containerization.

The project plan prioritizes measurable milestones and technical dependencies so that each stage produces an artifact required by the next. By the end of the internship, the expected outcome is not simply a trained model but a documented, testable, deployable ML prototype that demonstrates practical readiness for an entry-level Machine Learning Engineer role.

# 17. References and Suggested Public Resources

scikit-learn documentation – Feature extraction, text processing and evaluation metrics: https://scikit-learn.org/

Hugging Face documentation – Transformers and sentence-transformer ecosystem: https://huggingface.co/docs

Sentence Transformers documentation – Semantic textual similarity and embeddings: https://www.sbert.net/

FastAPI documentation – API development and validation: https://fastapi.tiangolo.com/

Docker documentation – Containerization and deployment: https://docs.docker.com/

spaCy documentation – Industrial-strength NLP and entity extraction: https://spacy.io/

PyMuPDF documentation – PDF processing and text extraction: https://pymupdf.readthedocs.io/

# 18. Final Submission Checklist

☐ Research and literature review completed

☐ Problem domain and problem statement finalized

☐ Inputs, outputs, scope and limitations documented

☐ Six-week timeline and milestones completed

☐ Critical path and dependencies documented

☐ Dataset sources and data-processing strategy documented

☐ Baseline and semantic ML approaches implemented

☐ Evaluation metrics and acceptance criteria defined

☐ Resource requirements documented

☐ Risk register and mitigation plan completed

☐ FastAPI service implemented and tested

☐ Docker deployment completed

☐ Technical documentation and repository organized

☐ Final demonstration and presentation prepared

☐ Word Table of Contents updated before submission